## Participant
HT-AJAW-B26 | Prajakta Chandrakant Borhade | 2203154 | PrajaktaChandrakant.Borhade@cognizant.com
HT-AJAW-B26 | Lavanya B | 2203379 | Lavanya.B9@cognizant.com
HT-AJAW-B26 | Udhaya Kumar J | 2203857 | UdhayaKumar.J@cognizant.com
HT-AJAW-B26 | A Chennakesavulu | 2203859 | A.Chennakesavulu@cognizant.com
HT-AJAW-B26 | Sai Lakshmi Nath Kaligineedi | 2204423 | SaiLakshmiNath.Kaligineedi@cognizant.com
HT-AJAW-B26 | Ganti Karthikeya | 2204366 | Ganti.Karthikeya@cognizant.com
HT-AJAW-B26 | Mandem Girish Reddy | 2204491 | MandemGirish.Reddy@cognizant.com
HT-AJAW-B26 | Kirtishil Dhiwar | 2204293 | Kirtishil.Dhiwar@cognizant.com
HT-AJAW-B26 | P Praveen Reddy | 2205543 | PPraveen.Reddy@cognizant.com
HT-AJAW-B26 | Bhavesh Agrawal | 2205399 | Bhavesh.Agrawal@cognizant.com
HT-AJAW-B26 | Ashwini C | 2205510 | Ashwini.C5@cognizant.com
HT-AJAW-B26 | Virupaksha R D | 2205316 | Virupaksha.RD@cognizant.com
HT-AJAW-B26 | Deepthi Acharya | 2205299 | Deepthi.Acharya@cognizant.com
HT-AJAW-B26 | Harshwardhan Kumar | 2190577 | Harshwardhan.Kumar@cognizant.com

## Sheet2
|  |  | 19th Jul 2022 |  | 20th Jul
Prajakta Chandrakant Borhade | 2203154 | PrajaktaChandrakant.Borhade@cognizant.com | Using mobile network, not possible to continue with the presentation |  | No update
Lavanya B | 2203379 | Lavanya.B9@cognizant.com | A crud Monolithic application with flight resource Pending areas: * Microservcie architecture not started yet * Swagger * Spring Security with JWT * Kafka - User can not --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can not --- add flight --- block/unblock flight Improvement areas: - Poor performance - Need to work on basics of springboot, rest applications - Never had any interaction with mentor during session | Udhaya Kumar J | No update
Udhaya Kumar J | 2203857 | UdhayaKumar.J@cognizant.com | A crud Monolithic application with flight resource Pending areas: * Microservcie architecture not started yet * Swagger * Spring Security with JWT * Kafka - User can not --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can not --- add flight --- block/unblock flight Improvement areas: - Poor performance - Need to work on basics of springboot, rest applications - Never had any interaction with mentor during session | Lavanya B | No update
A Chennakesavulu | 2203859 | A.Chennakesavulu@cognizant.com | * Microservcie architecture * Swagger * Completed tasks -- User registration -- User login -- User can see all flight -- Airport service Pending areas: * Spring Security with JWT * Kafka - User can not --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can not --- add flight --- block/unblock flight Improvement areas: - Average performance - Should go through the documetation before implementing features - Focus on design and analysis |  | - Admin can --- add flight --- block/unblock flight
Sai Lakshmi Nath Kaligineedi | 2204423 | SaiLakshmiNath.Kaligineedi@cognizant.com | Absent |  | No update
Ganti Karthikeya | 2204366 | Ganti.Karthikeya@cognizant.com | * Microservcie architecture * Completed tasks - User can --- search flight --- book flight - Admin can --- add flight Pending areas: * Spring Security with JWT * Kafka * Swagger - User can not --- see history by email --- see ticket by pnr --- cancel ticket - Admin can not --- block/unblock flight Improvement areas: - need to work on flight booking logic - Overall average performance |  | Admin can - block/unblock flights * Swagger is complete * Spring security with jwt -- started implementing
Mandem Girish Reddy | 2204491 | MandemGirish.Reddy@cognizant.com | * Microservcie architecture * Completed tasks - User can --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket ------ getting problem - Admin can --- add flight Pending areas: * Spring Security with JWT * Kafka * Swagger - Admin can not --- block/unblock flight Improvement areas: - Better than average performance - start learning spring security and kafka |  | Admin can - block/unblock flights * Spring security with jwt -- going to start today * No update for kafka
Kirtishil Dhiwar | 2204293 | Kirtishil.Dhiwar@cognizant.com | - Not able to implement any thing, due to health issues - Need more time to complete project - Microservice architecture is ready - Swagger is used |  | No update
P Praveen Reddy | 2205543 | PPraveen.Reddy@cognizant.com | * Microservcie architecture * Completed tasks - Admin can --- add flight Pending areas: * Spring Security with JWT * Kafka * Swagger - User can not --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can not --- block/unblock flight Improvement areas: - Average performance - Start learning spring security and kafka |  | No update
Bhavesh Agrawal | 2205399 | Bhavesh.Agrawal@cognizant.com | * Microservcie architecture * Spring Security with JWT * Swagger * Completed tasks - User can --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can --- add flight --- block/unblock flight Pending areas: * Kafka * Very good performance * Improvement areas: - should start learning kafka |  | No update
Ashwini C | 2205510 | Ashwini.C5@cognizant.com | * Monolithic application * Completed tasks - User can --- search flight --- book flight Pending areas: * Microservcie architecture * Kafka * Swagger * Spring Security with JWT - User can not --- see history by email --- see ticket by pnr --- cancel ticket - Admin can not --- add flight --- block/unblock flight Improvement areas: - poor performance - should start implement --- kafka --- spring security --- swagger --- microservice |  | No update
Virupaksha R D | 2205316 | Virupaksha.RD@cognizant.com | * Microservcie architecture * Spring Security with JWT * Completed tasks - User can --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can --- add flight --- block/unblock flight Pending areas: * Kafka * Swagger * Very good performance * Improvement areas: - should start implement --- kafka --- swagger |  | No update
Deepthi Acharya | 2205299 | Deepthi.Acharya@cognizant.com | * Microservcie architecture * Spring Security with JWT * Swagger * Completed tasks - User can --- search flight --- book flight --- see history by email --- see ticket by pnr --- cancel ticket - Admin can --- add flight --- block/unblock flight Pending areas: * Kafka * very good performance * Improvement areas: - should start implement --- kafka |  | No update
Harshwardhan Kumar | 2190577 | Harshwardhan.Kumar@cognizant.com | - Not able to implement any thing, due to health issues - Need more time to create project |  | No update